## Sheet1
CONTROLO DO PROJETO E GESTÃO DO ESFORÇO E PRODUTIVIDADE DA EQUIPA
EQUIPA: |  |  |  | DATA DE REVISÃO DO PLANO: | [7 empty] | TOTAL VERIF: |  |  |  |  | 1250 |  |  |  | H
|  |  |  | VERSÃO |  | DATA: | [5 empty] | MAX.: |  |  |  |  | 2100 |  |  |  | H |  |  | ECTS |  | 15 | H-ECTS |  | 28 | EQUIPA | 5 | TX FOLGA | 0.3
| André Roda dos Santos Oliveira |  |  | 48633 | [7 empty] | EFECT. |  |  |  |  | 1470 |  |  |  | H |  |  | Nota: Margem de 33% de não produtividade efectiva
| Alexander Pavlovich Denisov |  |  | 44592 |  | 2020-05-15 | [5 empty] | CONTROLO DE PRODUTIVIDADE: | [8 empty] | REF.
| Alexandre David Projecto Mendes |  |  | 42043 |  | 2020-05-15 | [5 empty] | MÉTRICAS |  |  |  |  | SEMANA |  |  | 3 |  |  |  | OBS)
| Edson Jorge Mendes Sousa |  |  | 43532 |  | 2020-05-15 | [5 empty] | RÁCIO DE PROD. MÉDIA |  |  |  |  | 89.2857 |  |  | /S | 105
| Sara Afonso Ferreira Trafaria |  |  | 41693 |  | 2020-05-15 | [5 empty] | EXECUÇÃO DO ESFORÇO: |  |  |  |  | 85.03% |  |  | % | 100%
|  |  |  | Aluno Nº | [7 empty] | ESFORÇO DISPONÍVEL: |  |  |  |  | -1030.8267 |  |  | H | HORAS
| OBS: | [10 empty] | OBS)
| ATIVIDADES DA EQUIPA |  | ABRIL |  |  |  | MAIO | [7 empty] | JUN | [9 empty] | JUL | [5 empty] | CONTR | CONTR
|  |  | S3 |  | S4 |  | S5 |  | S6 |  | S7 |  | S8 |  | S9 |  | S10 |  | S11 |  | S12 |  | S13 |  | S14 |  | S15 |  | S14 |  | HORAS | %
|  |  | 20 | 24 | 27 | 1/5 | 4 | 8 | 11 | 15 | 18 | 22 | 25 | 30 | 1 | 5 | 8 | 12 | 15 | 19 | 22 | 26 | 29 | 3/7 | 6 | 10 | 13 | 17 | 20 | 27
| TAREFA | DESIGNAÇÃO DA TAREFA | [5 empty] | Prep ALFA | ALFA (13/5) | [6 empty] | Prep BETA |  | BETA (14/6) | [6 empty] | Prep PP |  | Prep PROD | P.PROD (19/7)
WP1 | T1 | Construção operação de Registo e Login | [28 empty] | 0 | 0%
| T1.1 | Servidor | 8 | [5 empty] | 4 |  | 6 |  |  |  | 3 |  |  |  | 2 | [5 empty] | 2 |  |  |  | 2 |  | 27 | 1.837%
| T1.2 | Browser | 14 |  | 6 |  |  |  | 8 |  | 8 |  |  |  | 4 |  |  |  | 2 | [5 empty] | 2 |  |  |  | 2 |  | 46 | 3.129%
| T1.3 | Android | 8 | [5 empty] | 6 |  | 6 |  |  |  | 4 |  |  |  | 2 | [5 empty] | 2 |  |  |  | 2 |  | 30 | 2.041%
| T2 | Implementação de Mapas | [28 empty] | 0 | 0%
| T2.1 | Servidor |  |  | 8 |  |  |  | 8 |  | 9 | [7 empty] | 2 |  | 3 |  | 2 |  | 2 |  | 2 |  | 2 |  | 38 | 2.585%
| T2.2 | Browser | 8 |  | 6 |  | 8 |  | 4 |  | 12 | [7 empty] | 2 |  | 6 |  | 4 |  | 2 |  | 4 |  | 3 |  | 59 | 4.014%
| T2.3 | Android | 8 |  | 6 |  |  |  | 2 |  | 12 |  |  |  | 3 |  |  |  | 2 |  | 4 |  | 2 |  | 2 |  | 2 |  | 2 |  | 45 | 3.061%
| T3 | Definir percursos | [28 empty] | 0 | 0%
| T3.1 | Servidor |  |  | 12 |  | 6 |  | 8 | [5 empty] | 2 |  |  |  | 2 | [5 empty] | 2 |  |  |  | 2 |  | 34 | 2.313%
| T3.2 | Browser |  |  | 8 |  | 12 |  | 7 | [9 empty] | 2 | [5 empty] | 2 |  |  |  | 2 |  | 33 | 2.245%
| T3.3 | Android |  |  | 9 | [9 empty] | 6 |  |  |  | 2 | [5 empty] | 2 |  |  |  | 2 |  | 21 | 1.429%
WP1 | T4 | Editar percursos | [28 empty] | 0 | 0%
| T4.1 | Servidor |  |  |  |  | 4 | [7 empty] | 4 |  |  |  | 2 |  | 4 |  | 2 |  | 2 |  |  |  | 2 |  | 20 | 1.361%
| T4.2 | Browser |  |  | 9 |  | 8 |  | 10 | [5 empty] | 4 |  |  |  | 2 |  | 6 |  | 4 |  | 2 |  |  |  | 2 |  | 47 | 3.197%
| T4.3 | Android |  |  | 7 | [9 empty] | 5 |  |  |  | 2 |  | 6 |  | 4 |  | 2 |  |  |  | 2 |  | 28 | 1.905%
| T5 | Utilização off-line | [28 empty] | 0 | 0%
| T5.1 | Servidor | [14 empty] | 6 |  | 2 |  | 6 |  | 4 |  | 2 |  | 3 |  | 2 |  | 25 | 1.701%
| T5.2 | Browser | [28 empty] | 0 | 0%
| T5.3 | Android | [14 empty] | 8 |  | 2 |  | 8 |  | 6 |  | 4 |  | 3 |  | 2 |  | 33 | 2.245%
| T6 | Área de utilizador (Profile) | [28 empty] | 0 | 0%
| T6.1 | Servidor | 12 |  |  |  | 10 |  |  |  | 3 | [7 empty] | 2 | [5 empty] | 2 |  | 4 |  | 2 |  | 35 | 2.381%
| T6.2 | Browser | 8 |  |  |  | 6 |  | 12 |  | 16 | [7 empty] | 2 | [5 empty] | 2 |  | 6 |  | 4 |  | 56 | 3.81%
| T6.3 | Android | 6 | [5 empty] | 8 |  | 6 | [7 empty] | 2 | [5 empty] | 2 |  | 4 |  | 2 |  | 30 | 2.041%
WP1 | T7 | Comunidade | [28 empty] | 0 | 0%
| T7.1 | Servidor | [10 empty] | 8 |  | 6 |  | 4 |  | 2 | [5 empty] | 2 |  | 2 |  | 2 |  | 26 | 1.769%
| T7.2 | Browser |  |  |  |  | 6 | [5 empty] | 14 |  | 10 |  | 8 |  | 6 | [5 empty] | 2 |  | 6 |  | 4 |  | 56 | 3.81%
| T7.3 | Android | [10 empty] | 10 |  | 3 |  | 6 |  | 2 | [5 empty] | 2 |  | 4 |  | 2 |  | 29 | 1.973%
| T8 | Identificação de zonas de risco | [28 empty] | 0 | 0%
| T8.1 | Servidor | [10 empty] | 8 |  | 8 |  | 4 |  | 2 |  |  |  | 6 |  | 4 |  | 2 |  | 2 |  | 36 | 2.449%
| T8.2 | Browser | [10 empty] | 14 |  | 12 |  | 10 |  | 6 |  |  |  | 8 |  | 6 |  | 4 |  | 2 |  | 62 | 4.218%
| T8.3 | Android | [10 empty] | 6 |  | 3 |  | 8 |  | 2 |  |  |  | 6 |  | 4 |  | 2 |  | 2 |  | 33 | 2.245%
| T9 | Moderação da Comunidade | [28 empty] | 0 | 0%
| T9.1 | Servidor | [10 empty] | 10 |  | 8 |  | 6 |  | 2 | [5 empty] | 2 |  | 3 |  | 3 |  | 34 | 2.313%
| T9.2 | Browser | [10 empty] | 16 |  | 14 |  | 10 |  | 2 | [5 empty] | 2 |  | 6 |  | 4 |  | 54 | 3.673%
| T9.3 | Android | [14 empty] | 10 |  | 2 | [5 empty] | 2 |  | 4 |  | 3 |  | 21 | 1.429%
| T10 | Registo de participação | [28 empty] | 0 | 0%
| T10.1 | Servidor | [16 empty] | 6 |  | 6 |  | 4 |  | 2 |  | 1 |  | 2 |  | 21 | 1.429%
| T10.2 | Browser | [28 empty] | 0 | 0%
| T10.3 | Android | [16 empty] | 6 |  | 6 |  | 4 |  | 2 |  | 1 |  | 2 |  | 21 | 1.429%
WP1 | T11 | Criação de GeoStops | [28 empty] | 0 | 0%
| T11.1 | Servidor |  |  |  |  | 12 |  | 8 |  | 12 | [5 empty] | 6 |  | 2 | [5 empty] | 2 |  |  |  | 2 |  | 44 | 2.993%
| T11.2 | Browser |  |  |  |  | 18 |  | 15 |  | 11 | [5 empty] | 12 |  | 2 | [5 empty] | 2 |  |  |  | 2 |  | 62 | 4.218%
| T11.3 | Android | [10 empty] | 8 |  |  |  | 10 |  | 2 | [5 empty] | 2 |  |  |  | 2 |  | 24 | 1.633%
| T12 | Publicidade nos percursos | [28 empty] | 0 | 0%
| T12.1 | Servidor | [18 empty] | 12 |  | 10 |  | 6 |  | 4 |  | 3 |  | 35 | 2.381%
| T12.2 | Browser | [18 empty] | 16 |  | 14 |  | 10 |  | 8 |  | 6 |  | 54 | 3.673%
| T12.3 | Android | [18 empty] | 10 |  | 8 |  | 6 |  | 4 |  | 3 |  | 31 | 2.109%
| CONTROLO DE EQUIPA*SEMANA |  | 72 |  | 71 |  | 90 |  | 100 |  | 101 |  | 94 |  | 99 |  | 108 |  | 78 |  | 93 |  | 88 |  | 94 |  | 79 |  | 83 |  | 1250 | 82.67%
| REF Média de HORAS EQUIPA * SEMANA |  | 108 |  | 108 |  | 108 |  | 108 |  | 108 |  | 108 |  | 108 |  | 108 |  | 108 |  | 108 |  | 108 |  | 108 |  | 108 |  | 108 |  | 1512 | 100%
|  | REF Máx. Esforço Equipa H * Semana | 125 |  | 125 |  | 125 |  | 125 |  | 125 |  | 125 |  | 125 |  | 125 |  | 125 |  | 125 |  | 125 |  | 125 |  | 125 |  | 125 |  | 1750 | 115.7%
PERFIS DE DESDOBRAMENTO DA EQUIPA
| P1 | Project Management | 7 |  | 4 | [7 empty] | 7 |  | 4 | [5 empty] | 7 |  | 4 |  |  |  | 7 |  |  |  | 40 | 2.721%
| P2 | Project Documentation and Dissemination Mat. |  |  | 3 | [9 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 |  |  |  | 12 | 0.8163%
| P3 | Specification and Requirements Analyst | 3 |  | 4 | [7 empty] | 3 |  | 4 | [5 empty] | 3 |  | 4 |  |  |  | 8 |  |  |  | 29 | 1.973%
| P4 | WEB (JS-AJAX) UI Development |  |  |  |  | 8 | [7 empty] | 8 | [5 empty] | 8 | [9 empty] | 24 | 1.633%
| P5 | Android App / Interface Des. Developer |  |  |  |  | 4 | [23 empty] | 4 | 0.2721%
| P6 | Google Platform (Engine) Developer |  |  | 6 | [9 empty] | 6 | [5 empty] | 3 | [9 empty] | 15 | 1.02%
| P7 | Google Storage Services Developer |  |  | 6 | [9 empty] | 6 | [5 empty] | 3 | [9 empty] | 15 | 1.02%
| P8 | SW Architect / Architectural Requirements |  |  | 8 | [9 empty] | 8 | [5 empty] | 4 | [9 empty] | 20 | 1.361%
| P9 | Unitary / Partial Tests (Tester) | [14 empty] | 12 | [5 empty] | 12 |  |  |  | 12 |  |  |  | 36 | 2.449%
| P10 | Integration Tests (Tester) | [14 empty] | 12 | [5 empty] | 12 |  |  |  | 12 |  |  |  | 36 | 2.449%
| P11 | SW Architectural Tests / Arch. Requirements | [14 empty] | 10 | [5 empty] | 10 |  |  |  | 10 |  |  |  | 30 | 2.041%
| P12 | Product Staging and Testing Cordination | [14 empty] | 8 | [5 empty] | 8 |  |  |  | 8 |  |  |  | 24 | 1.633%
| P13 | Project Presentation |  |  |  |  | 6 |  | 40 |  | 20 | [5 empty] | 3 |  | 43 |  | 20 |  |  |  | 40 | [5 empty] | 172 | 11.7%
| P14 | Marketing (Blogue) |  |  |  |  | 2 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  |  |  | 9 | 0.6122%
| P15 | Meetings |  |  |  |  | 20 | [5 empty] | 25 |  |  |  | 20 | [5 empty] | 20 |  |  |  | 20 |  |  |  | 105 | 7.143%
| ?? | [29 empty] | 0 | 0%
| ?? | [29 empty] | 0 | 0%
| TOTAL: |  | 10 |  | 31 |  | 40 |  | 40 |  | 21 |  | 36 |  | 40 |  | 66 |  | 43 |  | 52 |  | 71 |  | 40 |  | 81 |  | 0 |  | 571 | 38.84%
Inclua a seguir (ou como anexo) uma representação GANTT do Plano